## task level
step | task |  | date | status | notes
0 | set up heroku and browser template |  | 2017-04-25 | completed
1 | spin up back end |  | 2017-04-25 | completed
2 | spin up front end |  | 2017-04-25 | completed
3 | meet with Scott re: plan for proj 2 setup |  | 2017-04-26 | completed | outstanding question re: master branch name for client
4 | Set up rails files for Entry table |  | 2017-04-26 | completed
5 | Review One to Many and Rails API |  | 2017-04-26 | completed
6 | Create files for entries (not users) |  | 2017-04-27 | completed
bin/rails generate scaffold entry title:string backstory:string stopper:string status:string date_added:timestamp deleted_flag: boolean
|  | review routes file | updated for restful
|  | review migration files | reviewed, didn't update
|  | review model files | reviewed, updated with validations
|  | review controller files | updated
|  | review serializer files | updated - deleted_flag doesn't need to display
7 | Make updates to files for entries | make any applicable changes to files | 2017-04-27 | completed | see rows 9-14
8 | Create curl requests
|  | user sign up | 2017-04-27 | completed
|  | user sign in | 2017-04-27 | completed
|  | user change password | 2017-04-27 | completed
|  | user sign out | 2017-04-27 | completed
|  | entry create | 2017-04-27 | completed
|  | entry show all | 2017-04-27 | completed
|  | entry show one | 2017-04-27 | completed
|  | entry update | 2017-04-27
|  | entry delete | 2017-04-27 | completed
9 | Set up association between entries and users |  | 2017-04-27
(optional) | Create seed file for entries |  | 2017-04-27
15 | create index.html |  | 2017-04-27
16 | create index.scss |  | 2017-04-27
17 | create js files/handlebars
18 | README for back-end
19 | README for front-end
20 | test authentication
21 | test entrie CRUD from UI
22 | update UI to make it look pretty
23 | ask friends/fam to test

## high level
2017-04-25 | begin building api
update user stories
update wireframes
2017-04-26 | continue building api
2017-04-27 | begin building front end
2017-04-28 | continue building front end
2017-04-29 | make sure front end/back end are working
2017-04-30 | finish/polish front end
2017-05-01 | testing, edit
2017-05-02 | testing
2017-05-03 | present

## notes
4/26 discussed project set up with Scott. Should skip testing stuff that we learned today for now.
user db is set up, no need to do that
per Scott,
create database for entries
generate scaffold for entries
review files and edit
migrate
bin/rake test runs automated tests.
bin/rails console opens a REPL that pre-loads the API.
bin/rails db opens your database client and loads the correct database.
bin/rails server starts the API.
scripts/*.sh run various curl commands to test the API. See below.
bin/rails db:create
bin/rails db:migrate
update model for has many
update model for belongs to
create examples file
bin/rake db:examples
bin/rails generate migration
bin/rails db:migrate
bin/rails console to create relationships in pry

## DB & table info
entries table should look like:
entry_id | title (:string) | backstory (string) | stopper (:string) | status (:string) | delete_flag (:boolean) | user_id
users table should look like:
id | email (char varying) | token (char varying) | password_digest (char varying) | created_at (:timestamp) | updated_at (:timestamp) | last_logged_in (:timestamp)
ROUTES
Prefix Verb URI Pattern Controller#Action
sign_up POST /sign-up(.:format) users#signup
sign_in POST /sign-in(.:format) users#signin
DELETE /sign-out/:id(.:format) users#signout
PATCH /change-password/:id(.:format) users#changepw
users GET /users(.:format) users#index
examples table should look like:
id (:integer) | text (:text) | user_id (:integer) | created_at (:timestamp) | updated_at: (:timestamp)
ROUTES
Prefix Verb URI Pattern Controller#Action
examples GET /examples(.:format) examples#index
POST /examples(.:format) examples#create
example GET /examples/:id(.:format) examples#show
PATCH /examples/:id(.:format) examples#update
PUT /examples/:id(.:format) examples#update
DELETE /examples/:id(.:format) examples#destroy