## task level
step | task |  | day | date | status | notes
0 | set up heroku and browser template |  | Tuesday | 2017-04-25 | completed
1 | spin up back end |  | Tuesday | 2017-04-25 | completed
2 | spin up front end |  | Tuesday | 2017-04-25 | completed
3 | meet with Scott re: plan for proj 2 setup |  | Wednesday | 2017-04-26 | completed | outstanding question re: master branch name for client
4 | Set up rails files for Entry table |  | wednesday | 2017-04-26 | completed
5 | Review One to Many and Rails API |  | wednesday | 2017-04-26 | completed
6 | Create files for entries (not users) |  | Thursday | 2017-04-27 | completed
|  | bin/rails generate scaffold entry title:string backstory:string stopper:string status:string date_added:timestamp deleted_flag: boolean | Thursday
|  | review routes file | Thursday | updated for restful
|  | review migration files | Thursday | reviewed, didn't update
|  | review model files | Thursday | reviewed, updated with validations
|  | review controller files | Thursday | updated
|  | review serializer files | Thursday | updated - deleted_flag doesn't need to display
7 | Make updates to files for entries | make any applicable changes to files | Thursday | 2017-04-27 | completed | see rows 9-14
8 | Create curl requests |  | Thursday
|  | user sign up | Thursday | 2017-04-27 | completed
|  | user sign in | Thursday | 2017-04-27 | completed
|  | user change password | Thursday | 2017-04-27 | completed
|  | user sign out | Thursday | 2017-04-27 | completed
|  | entry create | Thursday | 2017-04-27 | completed
|  | entry show all | Thursday | 2017-04-27 | completed
|  | entry show one | Thursday | 2017-04-27 | completed
|  | entry update | Thursday | 2017-04-28 | completed
|  | entry delete | Thursday | 2017-04-27 | completed
9 | Set up association between entries and users |  | Thursday | 2017-04-27 | completed
(optional) | Create seed file for entries |  | Friday | 2017-04-28 | in progress
15 | create index.html |  | Friday | 2017-04-28 | completed
|  | create section for authentication | Friday | 2017-04-28 | completed
|  | add buttons for authentication | Friday | 2017-04-28 | completed
16 | create index.scss |  | Friday | 2017-04-28 | completed
17 | create js files/handlebars |  | Friday | 2017-04-28 | in progress
18 | add functionality for authentication
|  | sign up functionality | Friday | 2017-04-30 | completed
|  | sign in functionality | Friday | 2017-04-30 | completed
|  | sign out functionality | Friday | 2017-04-30 | completed
|  | change password functionality | Friday | 2017-04-30 | completed
19 | add functionality for hopes and dreams |  | Friday/Saturday | 2017-04-28
|  | create section for hopes and dreams | Friday/Saturday | 2017-04-29 | completed
|  | add buttons for hopes and dreams | Friday/Saturday | 2017-04-29 | completed
|  | show all - default | Friday/Saturday | 2017-04-29 | in progress
|  | show one | Friday/Saturday | 2017-04-29 | in progress
|  | update one hope and dream | Friday/Saturday | 2017-04-29 | in progress
|  | hide 1 hope and dream | Friday/Saturday | 2017-04-29 | in progress
|  | remove 1 hope and dream completely | Friday/Saturday | 2017-04-29 | in progress
20 | connect authent with back end |  | Friday | 2017-04-28
21 | connect entries with back end |  | Friday | 2017-04-28
22 | fix/continue with connection |  | Saturday | 2017-04-29
23 | polish index.html |  |  | 2017-04-29
24 | polish index.scss |  | Friday | 2017-04-29
25 | polish handlebars |  | Friday | 2017-04-29
26 | README for back-end |  | Sunday | 2017-04-29
27 | README for front-end |  | Sunday | 2017-04-29
28 | test authentication
29 | test entrie CRUD from UI
30 | update UI to make it look pretty
31 | ask friends/fam to test

## high level
2017-04-25 | begin building api
update user stories
update wireframes
2017-04-26 | continue building api
2017-04-27 | begin building front end
2017-04-28 | continue building front end
2017-04-29 | make sure front end/back end are working
2017-04-30 | finish/polish front end
2017-05-01 | testing, edit
2017-05-02 | testing
2017-05-03 | present

## notes
4/26 discussed project set up with Scott. Should skip testing stuff that we learned today for now.
After receiving the project prompt, decide what kind of app to make, and begin sketching some rough wireframes for how the front end will look and act.
user db is set up, no need to do that |  | Think about what kind of data your front-end will need from your back-end, and how that data will be used. Create an ERD.
Create two repos that your project will use, and add READMEs to both.
per Scott, |  | Create a simple front-end with HTML and CSS based (loosely) on your wireframes.
| create database for entries | User our rails-api-template for your back-end. It already includes authentication.
| generate scaffold for entries | After you have an ERD, check with a consultant to ensure your data model is appropriate for your goals. Then, build the models and migrations to represent this data. Test your models using the Rails console, and test your API endpoints using curl. You may also write automated tests in RSpec if you choose.
| review files and edit | Before working on the front-end application, ensure all back-end endpoints work as expected. Knowing the back-end well will help you diagnose bugs on the front-end.
| migrate | Write your front-end application using JavaScript, jQuery, and AJAX.
Test, commit, and deploy often! Test, commit, deploy! Test your deployments!
When main features are finished, begin working on stretch goals and icebox features.
bin/rake test runs automated tests. |  | Finish your documentation. Make it high-quality.
bin/rails console opens a REPL that pre-loads the API.
bin/rails db opens your database client and loads the correct database.
bin/rails server starts the API. |  | Tips
scripts/*.sh run various curl commands to test the API. See below. |  | Begin with the end in mind. Know where you want to go by planning with wireframes and user stories, so you don't waste time designing and building things you don't need.
Remember that your backend environment is different from your browser environment – use tools to help you visualize it.
Don’t hesitate to write throwaway code to solve short term problems.
bin/rails db:create |  | Read the docs for whatever technologies / frameworks / API’s that you use. Most of the time, there is a tutorial that you can follow, but not always, and learning to read documentation is crucial to your success as a developer.
bin/rails db:migrate |  | Commit early, commit often. As long as you do that, you don’t be afraid about breaking something, because you can always go back in time to a previous version. Always work on a branch!
update model for has many |  | User stories define what a user wants to accomplish with your application. It's tempting to just make them todo lists for what needs to get done, but if you keep them small and focused on the user's needs, it'll help you know what to build.
update model for belongs to |  | Write pseudocode before you write actual code. Thinking through the logic of something helps.
create examples file |  | Finally, here are some resources that it might be good for you to look at/read about:
bin/rake db:examples |  | Heroku Documentation
bin/rails generate migration |  | Writing Good User Stories
bin/rails db:migrate |  | Presenting Information Architecture
bin/rails console to create relationships in pry |  | Good luck and happy hacking!

## DB & table info
entries table should look like:
entry_id | title (:string) | backstory (string) | stopper (:string) | status (:string) | delete_flag (:boolean) | user_id
users table should look like:
id | email (char varying) | token (char varying) | password_digest (char varying) | created_at (:timestamp) | updated_at (:timestamp) | last_logged_in (:timestamp)
ROUTES
Prefix Verb URI Pattern Controller#Action
sign_up POST /sign-up(.:format) users#signup
sign_in POST /sign-in(.:format) users#signin
DELETE /sign-out/:id(.:format) users#signout
PATCH /change-password/:id(.:format) users#changepw
users GET /users(.:format) users#index
examples table should look like:
id (:integer) | text (:text) | user_id (:integer) | created_at (:timestamp) | updated_at: (:timestamp)
ROUTES
Prefix Verb URI Pattern Controller#Action
examples GET /examples(.:format) examples#index
POST /examples(.:format) examples#create
example GET /examples/:id(.:format) examples#show
PATCH /examples/:id(.:format) examples#update
PUT /examples/:id(.:format) examples#update
DELETE /examples/:id(.:format) examples#destroy